## From Testing
BaseLine
BUS | Detail | 17:00 | 17:15 | 17:30 | 17:45 | 18:00 | 18:15 | 18:30 | 18:45 | 19:00 | 19:15 | 19:30 | 19:45 | 20:00 | 20:15 | 20:30 | 20:45 | 21:00 | 21:15 | 21:30 | 21:45 | 22:00 | 22:15 | 22:30 | 22:45 | 23:00 | 23:15 | 23:30 | 23:45 | 00:00 | 00:15 | 00:30 | 00:45 | 01:00 | 01:15 | 01:30 | 01:45
EOD IL | Clearing : 17:56 - 17:59 | [36 empty] | Note: Steps prepare : Not Run Process Step Not Run Process : Generate temp,Switch temp cashing,Auto receive online
| Change Date : 18:00 - 18:09 | [5 empty] | IL
EOD PW | Clearing : 17:56 - 18:47
| Change Date : 18:47 - 18:48 | [8 empty] | PW
EOD RL | Clearing : 17:56 - 20:14
Split OCRL (730 jobs) : 17:16 - 17:17
Process OCRL : 17:16 - 18:41
| Change​ Date : 20:17 - 20:38 | [13 empty] | RL
After Change​ Date : 20:38 - 21:15
EOD OB | Step Chang Date : 20:14 - 20:15 | [13 empty] | OB
Step Update Tel : 20:14 - 20:15
Step Flag Fulfill : 20:14 - 00:41
Dayend IS | IS_Main: 17:56 - 18:00 (0:04 Hrs.)
SSIS_Main: 18:01 - 18:09 (0:08 Hrs.)
Prepare_RL: 18:10 - 18:32 (0:22 Hrs.)
| IS_PH: 18:18 - 19:00 (0:38 Hrs.) |  |  |  |  | PH
SSIS_PH: 20:25 - 20:26 (0:01 Hrs.)
| IS_IL: 19:10 - 19:30 (0:20 Hrs.) | [8 empty] | IL
SSIS_IL:20:26-20:28 (0:02 Hrs.)
| IS_PW: 19:35-20:15 (0:40 Hrs.) | [10 empty] | PW
SSIS_PW: 20:31-20:33 (0:02 Hrs.)
SSIS_RL: 20:34-20:54 (0:20 Hrs.)
| IS_RL: 20:57-01:43 (04:45 Hrs.) | [16 empty] | RL
After
BUS | Detail | 10:00 | 10:15 | 10:30 | 10:45 | 11:00 | 11:15 | 11:30 | 11:45 | 12:00 | 12:15 | 12:30 | 12:45 | 13:00 | 13:15 | 13:30 | 13:45 | 14:00 | 14:15 | 14:30 | 14:45 | 15:00 | 15:15 | 15:30 | 15:45 | 16:00 | 16:15 | 16:30 | 16:45 | 17:00 | 17:15 | 17:30 | 17:45 | 18:00 | 18:15 | 18:30 | 18:45 | Note: Steps prepare : Not Run Process Step Not Run Process : Generate temp,Switch temp cashing,Auto receive online
EOD IL | Clearing : 10:28 - 10:32
| Change Date : 10:36 - 10:43 |  |  |  | IL
EOD PW | Clearing : 10:29 - 11:24
| Change Date : 11:24 - 11:25 | [6 empty] | PW
EOD RL | Clearing : 10:28 - 12:24
Split OCRL (730 jobs) : 10:57 - 10:58
Process OCRL : 10:57 - 12:18
| Change​ Date : 12:24 - 12:34 | [10 empty] | RL
After Change​ Date : 12:34 - 13:13
EOD OB | Step Chang Date : 12:19 - 12:20 | [9 empty] | OB
Step Update Tel : 12:20 - 12:21
Step Flag Fulfill : 12:20 - 16:59
Dayend IS | IS_Main: 10:29-10:33 ✅ (0:04 Hrs.)
SSIS_Main: 10:35-10:41 ✅ (0:06 Hrs.)
Prepare_RL: 10:43-10:52 ✅ (0:09 Hrs.)
| IS_PH: 10:43-11:17 ✅ (0:34 Hrs.) |  |  |  | PH
SSIS_PH: 11:19-11:19 ✅ (0:00 Hrs.)
| IS_IL: 11:25-11:48 ✅ (0:23 Hrs.) | [6 empty] | IL
SSIS_IL:11:51-11:52 ✅ (0:01 Hrs.)
| IS_PW: 11:53-12:43 ✅ (0:50 Hrs.) | [8 empty] | PW
SSIS_PW: 12:44-12:46 ✅ (0:02 Hrs.)
SSIS_RL: 12:47-13:01 ✅ (0:14 Hrs.)
| IS_RL: 13:11-16:31 ✅ (03:20 Hrs.) | [13 empty] | RL

## Compare Before & After
BaseLine
BUS | Detail | 23:00 | 23:15 | 23:30 | 23:45 | 24:00 | 24:15 | 24:30 | 24:45 | 25:00 | 25:15 | 25:30 | 25:45 | 26:00 | 26:15 | 26:30 | 26:45 | 27:00 | 27:15 | 27:30 | 27:45 | 28:00 | 28:15 | 28:30 | 28:45 | 29:00 | 29:15 | 29:30 | 29:45 | 30:00 | 30:15 | 30:30 | 30:45 | Note: Steps prepare : Not Run Process Step Not Run Process : Generate temp,Switch temp cashing,Auto receive online
EOD IL | Clearing : 17:56 - 17:59
| Change Date : 18:00 - 18:09 |  | IL
EOD PW | Clearing : 17:56 - 18:47
| Change Date : 18:47 - 18:48 |  |  |  |  | PW
EOD RL | Clearing : 17:56 - 20:14
Split OCRL (730 jobs) : 17:16 - 17:17
Process OCRL : 17:16 - 18:41
| Change​ Date : 20:17 - 20:38 | [9 empty] | RL
After Change​ Date : 20:38 - 21:15
EOD OB | Step Chang Date : 20:14 - 20:15 | [9 empty] | OB
Step Update Tel : 20:14 - 20:15
Step Flag Fulfill : 20:14 - 00:41
Dayend IS | IS_Main: 17:56 - 18:00 (0:04 Hrs.)
SSIS_Main: 18:01 - 18:09 (0:08 Hrs.)
Prepare_RL: 18:10 - 18:32 (0:22 Hrs.)
| IS_PH: 18:18 - 19:00 (0:38 Hrs.) | PH
SSIS_PH: 20:25 - 20:26 (0:01 Hrs.)
| IS_IL: 19:10 - 19:30 (0:20 Hrs.) |  |  |  |  | IL
SSIS_IL:20:26-20:28 (0:02 Hrs.)
| IS_PW: 19:35-20:15 (0:40 Hrs.) | [6 empty] | PW
SSIS_PW: 20:31-20:33 (0:02 Hrs.)
SSIS_RL: 20:34-20:54 (0:20 Hrs.)
| IS_RL: 20:57-01:43 (04:45 Hrs.) | [12 empty] | RL
After
BUS | Detail | 23:00 | 23:15 | 23:30 | 23:45 | 24:00 | 24:15 | 24:30 | 24:45 | 25:00 | 25:15 | 25:30 | 25:45 | 26:00 | 26:15 | 26:30 | 26:45 | 27:00 | 27:15 | 27:30 | 27:45 | 28:00 | 28:15 | 28:30 | 28:45 | 29:00 | 29:15 | 29:30 | 29:45 | 30:00 | 30:15 | 30:30 | 30:45 | Note: Steps prepare : Not Run Process Step Not Run Process : Generate temp,Switch temp cashing,Auto receive online
EOD IL | Clearing : 10:28 - 10:32
| Change Date : 10:36 - 10:43 |  | IL
EOD PW | Clearing : 10:29 - 11:24
| Change Date : 11:24 - 11:25 |  |  |  |  | PW
EOD RL | Clearing : 10:28 - 12:24
Split OCRL (730 jobs) : 10:57 - 10:58
Process OCRL : 10:57 - 12:18
| Change​ Date : 12:24 - 12:34 | [8 empty] | RL
After Change​ Date : 12:34 - 13:13
EOD OB | Step Chang Date : 12:19 - 12:20 | [7 empty] | OB
Step Update Tel : 12:20 - 12:21
Step Flag Fulfill : 12:20 - 16:59
Dayend IS | IS_Main: 10:29-10:33 ✅ (0:04 Hrs.)
SSIS_Main: 10:35-10:41 ✅ (0:06 Hrs.)
Prepare_RL: 10:43-10:52 ✅ (0:09 Hrs.)
| IS_PH: 10:43-11:17 ✅ (0:34 Hrs.) |  | PH
SSIS_PH: 11:19-11:19 ✅ (0:00 Hrs.)
| IS_IL: 11:25-11:48 ✅ (0:23 Hrs.) |  |  |  |  | IL
SSIS_IL:11:51-11:52 ✅ (0:01 Hrs.)
| IS_PW: 11:53-12:43 ✅ (0:50 Hrs.) | [6 empty] | PW
SSIS_PW: 12:44-12:46 ✅ (0:02 Hrs.)
SSIS_RL: 12:47-13:01 ✅ (0:14 Hrs.)
| IS_RL: 13:11-16:31 ✅ (03:20 Hrs.) | [11 empty] | RL
Result = เร็วขึ้น 35%

## Compare Before & After IS
BaseLine
BUS | Detail | 23:00 | 23:15 | 23:30 | 23:45 | 24:00 | 24:15 | 24:30 | 24:45 | 25:00 | 25:15 | 25:30 | 25:45 | 26:00 | 26:15 | 26:30 | 26:45 | 27:00 | 27:15 | 27:30 | 27:45 | 28:00 | 28:15 | 28:30 | 28:45 | 29:00 | 29:15 | 29:30 | 29:45 | 30:00 | 30:15 | 30:30 | 30:45
Dayend IS | IS_Main: 17:56 - 18:00 (0:04 Hrs.)
SSIS_Main: 18:01 - 18:09 (0:08 Hrs.)
Prepare_RL: 18:10 - 18:32 (0:22 Hrs.)
| IS_PH: 18:18 - 19:00 (0:38 Hrs.) | PH
SSIS_PH: 20:25 - 20:26 (0:01 Hrs.)
| IS_IL: 19:10 - 19:30 (0:20 Hrs.) |  |  |  |  | IL
SSIS_IL:20:26-20:28 (0:02 Hrs.)
| IS_PW: 19:35-20:15 (0:40 Hrs.) | [6 empty] | PW
SSIS_PW: 20:31-20:33 (0:02 Hrs.)
SSIS_RL: 20:34-20:54 (0:20 Hrs.)
| IS_RL: 20:57-01:43 (04:45 Hrs.) | [12 empty] | RL
Dayend IS | IS_Main: 10:29-10:33 ✅ (0:04 Hrs.)
SSIS_Main: 10:35-10:41 ✅ (0:06 Hrs.)
Prepare_RL: 10:43-10:52 ✅ (0:09 Hrs.)
| IS_PH: 10:43-11:17 ✅ (0:34 Hrs.) |  | PH
SSIS_PH: 11:19-11:19 ✅ (0:00 Hrs.)
| IS_IL: 11:25-11:48 ✅ (0:23 Hrs.) |  |  |  |  | IL
SSIS_IL:11:51-11:52 ✅ (0:01 Hrs.)
| IS_PW: 11:53-12:43 ✅ (0:50 Hrs.) | [6 empty] | PW
SSIS_PW: 12:44-12:46 ✅ (0:02 Hrs.)
SSIS_RL: 12:47-13:01 ✅ (0:14 Hrs.)
| IS_RL: 13:11-16:31 ✅ (03:20 Hrs.) | [11 empty] | RL
Result = เร็วขึ้น 29.8%

## Summary
Dayend IS – Comparison Summary |  | Metric | Before | After | Change | Process | Before (min) | After (min) | Δ (min) | Result
Total Duration (Before) : 7h 22m (442 mins) |  | Start Time | 17:56 | 18:01 | +5 min | IS_Main | 4 | 4 | 0 | No Change
Total Duration (After) : 5h 43m (343 mins) |  | End Time | 1:43 | 23:31 | ⬇ 2h12m | Prepare_RL | 22 | 9 | ⬇13 | Improved
Time Reduced : 99 mins |  | Total Duration | 7h22m | 5h43m | ⬇ 1h39m | IS_PH | 38 | 34 | ⬇4 | Improved
Improvement : 22.4 % |  | SLA | PASS | PASS | – | IS_IL | 20 | 23 | ⬆3 | Increased
[6 empty] | IS_PW | 40 | 50 | ⬆10 | Increased
[6 empty] | IS_RL | 285 | 200 | ⬇85 | Major Gain
Key Insights: • Overall Dayend IS reduced by 22.4%. • Significant improvement on IS_RL (−85 mins), the critical path.
Appendix
Before | After
Process IS | Process IS
As of 14/12/2025 Run at ESB-ASQL-04 | As of 14/12/2025 Run at ESB-ASQL-04
> IS _Main : 17:56-18:00✅(00:04Hrs.) | > IS _Main : 10:29-10:33✅(00:04Hrs.)
> SSIS Main : 18:01-18:09✅(00:08Hrs.) | > SSIS Main : 10:35-10:41✅(00:06Hrs.)
> Prepare RL : 18:10-18:32✅(00:22Hrs.) | > Prepare RL : 10:43-10:52✅(00:09Hrs.)
> IS_PH : 18:18-19:00✅(00:38Hrs.) | > IS_PH : 10:43-11:17✅(00:34Hrs.)
> SSIS_PH : 20:25-20:26✅(00:01Hrs.) | > SSIS_PH : 11:19-11:19✅(00:00Hrs.)
> IS_IL : 19:10-19:30✅(00:20Hrs.) | > IS_IL : 11:25-11:48✅(00:23Hrs.)
> SSIS_IL : 20:26-20:28✅(00:02Hrs.) | > SSIS_IL : 11:51-11:52✅(00:01Hrs.)
> IS_PW : 19:35-20:15✅(00:40Hrs.) | > IS_PW : 11:53-12:43✅(00:50Hrs.)
> SSIS_PW : 20:31-20:33✅(00:02Hrs.) | > SSIS_PW : 12:44-12:46✅(00:02Hrs.)
> SSIS_RL : 20:34-20:54✅(00:20Hrs.) | > SSIS_RL : 12:47-13:01✅(00:14Hrs.)
> IS_RL : 20:57-01:43✅(04:45Hrs.) | > IS_RL : 13:11-16:31✅(03:20Hrs.)
ก่อน = 7 ชั่วโมง 22 นาที = 442 นาที
หลัง = 5 ชั่วโมง 43 นาที = 343 นาที
ลดเวลาได้ 1 ชม. 39 นาที
เร็วขึ้นประมาณ 22.4%